## Work Packages
WP # | Name | Description | Key Activies | Time Estimation | Milestone | CAPEX | Requirement (CAR-NEED-xxxxx) | Expertise | Dependencies | Comments
1 | New rubber interface | Design, material, retention; mates multi-switch filter to Comms Adaptor rigid housing while preserving acoustic seal | CAD design files (rubber interface) | 3 wks design |  |  | 01001 | Mechanical / Design |  | Acoustics design review → concept phase verify Acoustics design review → before mould concept phase Before release, verify final design sealing and acoustics performance (Reference item)
Material spec
Iterative prototype samples
Tooling release
2 | New switch-mode filter | Improved cap: bare-finger tactile mode ID, reduced click noise fits DEC standard ear-tip; fits new rubber interface, middle mode is eliminated | New switch filter mode techincal specification | 8 wks design | Technical Specifications Signed |  | 01002, 01003 | Mechanical / Design; Acoustics |  | Tactile — how? What is an acceptable click level? Measure sound level of the current switch?
|  |  | CAD design files (cap + filter) |  | Tactile Validation report signed
Tactile validation report (bare-finger mode-ID success rate, user testing)
Click-noise measurement report (before/after vs. safety threshold)
Middle mode valiation report
Fit verification report (standard eartip + new rubber interface)
Prototype samples
Design release to tooling
3 | New tooling |  | Tooling for new rubber interface (iterative) | 6 wks (new rubber - mini unknowns) + 4wk iterations |  | 2 x injection moudliong 6k |  | Mechanical / Design | WP1, WP2, WP3
|  |  | Tooling Validation Report - New Rubb Interface | 1wk
|  |  | Tooling for new switch-mode filter | 6wks + 6 wks iterations
Tooling Validation Report - New Swithc Mode Filter
4 | Acoustic equivalence — test plan and execution against named baselines |  | Test plan with baseline configurations defined | 2wk |  | ARES - Acoustic Simulations - 5k | 02001, 02002, 02003 | Acoustics | WP1, WP2, WP3
|  |  | Create acoustic baseline based on the old swtich filter | 1wk
|  |  | Create a acoustic model of the current switch filter | 1wk
|  |  | Measure current tactile sound | 0.5wk
|  |  | Acoustic evaluation of prototype/final new rubber seal | 2 x 1wk
|  |  | Acoustic evaluation of prototype/final new switch filter | 2 x 1wk
|  |  | Equivalence test report — D2SIM Orange/ Blue / Beige | 1wk
|  |  | Equivalence test report — old switch-mode filter | 1wk
5 | Regulatory pathway | Ensuring no re-certifcation needed for new comms filter and new switch-mode filter; identify applicable EU standards - Per-octave-band 3 dB Only acoustics considered Manuals and marketing material updates | Standards landscape doc (EU / US / local) with coverage map | 2wk |  |  | 03001, 03002, 03004 | Quality | WP4 | What regulatory points are most relevant?
|  |  | Send filters for certiicaiton | PZT lead time — 6 wks
6 | Lifetime Verification | Aging behaviour of rubber insert; switch-cap durability; click consistency over life | Lifetime test plan | 14 wks 23 days = 1 year accelerated aging Clicking after lifetime? |  |  | 03003 | Mechanical / Materials | WP1, WP2, WP3 | Filter lifetime or switch? Request is open with Sonova
|  |  | Aging test report — rubber insert | 1wk
|  |  | Aging test report — switch cap (durability + click consistency + fitler????) | 1wk
7 | Manufacturing & tooling — manufacturability of new cap, housing, rubber insert; cavity strategy; phase-in / phase-out |  | Manufacturability assessment report |  |  |  | Additional from R&D | Manufacturing Engineering | WP1, WP2, WP3 | ME will not be responsible for moulding communication. ME involvement = production process planning.
Tooling consult - Cavity decision memo (2× vs 4× with cost & volume analysis)
8 | IP / patent landscape for new switch-cap design |  | IP / patent landscape report | FTO — 4 wks Additional from R&D |  |  |  | IP | WP2, WP3 | Note: numbered '9' in source — renumbered to 10 to avoid duplicate.
Freedom-to-operate analysis
9 | Usability and design review |  | Usability testing of newly developed rubber interface
Usablity study to determine an accetable sound level
Usablity study - tactile feeling of the new switch filter